## Projects
Client | Project | Start date | Due date | Status | Billing | Hours | Rate | Flat fee | Amount | Invoice sent | Paid on | Days left | Payment
Harbor Dental | Spring newsletter design | 2026-09-02 | 2026-09-19 | Done | Flat |  |  | 650 |  | 2026-09-19 | 2026-09-24
Pine & Co. Realty | Listing photo edits (batch 3) | 2026-09-08 | 2026-09-26 | In progress | Hourly | 6.5 | 55
Lakeside Yoga | Website copy refresh | 2026-09-15 | 2026-10-10 | In progress | Hourly | 3 | 60
Main St. Gift Shop | Holiday flyer | 2026-09-22 | 2026-10-03 | Not started | Flat |  |  | 300
Harbor Dental | Social media templates | 2026-08-18 | 2026-09-05 | Done | Flat |  |  | 480 |  | 2026-09-05
Formulas:
Days left = IF(OR([Due date]="",[Status]="Done"),"",[Due date]-TODAY())
Payment = IF([Paid on]<>"","Paid",IF([Invoice sent]="","Not invoiced",IF(TODAY()-[Invoice sent]>30,"Overdue","Waiting")))

## Summary
Open projects
Billed, not paid ($)
Paid ($)
Invoices overdue (30+ days)

## How to use
Tidy Tabs: Freelance Project Tracker
1. One row per project. Pick Status and Billing from the dropdowns.
2. Hourly jobs: fill Hours and Rate. Flat-fee jobs: fill Flat fee. Amount picks the right one.
3. Type the date you sent the invoice in Invoice sent, and the date the money arrived in Paid on.
4. Days left counts down to the due date (negative = late) and hides itself once Status is Done.
5. Payment shows Not invoiced / Waiting / Overdue (more than 30 days after you invoiced) / Paid.
6. Days left and Payment use TODAY(), so they change every day you open the file.
Sample clients are fictional. Delete rows 2-6 on the Projects tab to start fresh.
Google Sheets: File > Import > Upload this .xlsx.