## Plan
Chart starts on | 2026-11-02 | Fall market booth prep (fictional). Type dates as MM/DD/YYYY.
Task | Start | End | Days | Workdays | Tasks listed
Pick market and pay booth fee | 2026-11-02 | 2026-11-03 |  |  | Last day in the chart
Order tote bags and mugs | 2026-11-02 | 2026-11-06 |  |  | Tasks that run past the chart
Print signs and price tags | 2026-11-05 | 2026-11-09 |  |  | Check: every task has a name and valid dates
Build display shelves | 2026-11-09 | 2026-11-13
Pack inventory and cash box | 2026-11-16 | 2026-11-18
Test tent setup in driveway | 2026-11-17 | 2026-11-17
Market day | 2026-11-21 | 2026-11-22
Count sales and restock | 2026-11-23 | 2026-11-27

## How to use
Tidy Tabs: Simple Gantt Chart With One Conditional Formatting Rule
1. Plan tab: type the first day of the chart in B1, then each task (A), its start date (B) and end date (C). Yellow. Rows 4 to 23 are used. The sample is eight fictional tasks for a fall market booth.
2. The 28 date columns start in F3 (=$B$1, left blank if B1 is not a date) and each next one adds a day: G3 is =F3+1. Row 2 shows the weekday name from the date above it, in the format ddd.
3. Days, D4: =C4-B4+1 counts both the start and end day. Workdays, E4: =NETWORKDAYS(B4,C4) skips Saturday and Sunday. It does not know about holidays.
4. The bars are one conditional formatting rule applied to F4:AG23 with this formula: =AND(ISNUMBER($B4),ISNUMBER($C4),F$3>=$B4,F$3<=$C4). $B4 locks the column and F$3 locks the row, so one rule works for every cell. Weekend cells get a light gray fill from a second rule: =WEEKDAY(F$3,2)>5.
5. To make your own: select the grid, then Excel: Home > Conditional Formatting > New Rule > Use a formula to determine which cells to format; Google Sheets: Format > Conditional formatting > Custom formula is. Paste the formula for the first cell of your selection.
6. If an end date is before its start date, or a date is typed as text, D shows Check dates and no bar is drawn. The check cell AJ6 shows OK when every task has a name and two valid dates.
7. A task that runs past the 28th day is cut off at the edge of the chart; AJ5 counts them. Change B1 to move the chart.
8. There is no today line. TODAY() is not used, so the file never changes by itself.
Project and dates are fictional. Checked in LibreOffice Calc only; not opened in Excel or Google Sheets.
Google Sheets: File > Import > Upload this .xlsx (check that the conditional formatting came across).